## Actions
Action number | Activity | Date
AP.2015-1 | Everyone to review presentations etc that mention this group to ensure that it is written in full as CEOS-WGCV-IVOS. | Next meeting
AP.2015-2 | Nigel Fox to organise the formation of a new task group on PICS | WGCV meeting
AP.2015-3 | Françoise Viallefont to follow up the workshop on MTF and ensure that the database is collated and the data processing comparison is performed | Next meeting
AP.2015-4 | Nigel Fox to prepare formal response to the INSITU-OCR white paper and the IOCCG Report #13 | Their deadline
AP.2015-5 | Everyone to consider preparing articles for the GSICS newsletters, particularly on DCCs and lunar calibration | Their deadline
AP.2015-6 | Nigel Fox to ask GSICS to present on thermal infrared cross calibration methods at our next meeting | Next meeting
AP.2015-7 | Nigel Fox to organise discussions on SBAFs based on hyperspectral imager measurements bringing in GSICS and atmospheric sensor expertise, possibly as a WEBEX meeting. Kurt Thome to talk to the right people at NASA to support this. | Next meeting
AP.2015-8 | Nigel Fox to set up a meeting on solar irradiance spectrum, starting with discussions with GSICS-UV meeting | WGCV meeting
AP.2015-9 | Nigel Fox to organise a CEOS member discussion about the establishment of workshops on calibration coefficients | WGCV meeting
AP.2015-10 | Philippe Goryl to talk to Alessandro about the reasons for the problems with the CalVal portal and for him to set up a webex to encourage the subgroup to consider the communication strategy, newsletter and calval portal | WGCV meeting
AP.2015-11
AP.2015-12
AP.2015-13
AP.2015-14

## Recommendations
Decision number | Decision
R.2015-1 | IVOS recommends to WGCV that a PICS task group be set up to enhance collaboration and create a common work plan
R.2015-2 | IVOS recommends to WGCV the establishment of a reference dataset of CEOS recommended sites for MTF and to encourage agencies to collect data over these.
R.2015-3 | To establish a pilot project to carry out a comparison of inflight MTF retrieval methods through distribution of synthetic and real images
R.2015-4 | IVOS recommends to IOCCG the formation of a group to discuss pre-flight and onboard calibration needs. We feel that this should be through the CEOS-WGCV, though recognise that the needs of the OC community are demanding. | Not a recommendation, more a response to review
R.2015-5 | IVOS recommends the establishment of a depository/ database to collect information on the choice, values and rasons for the radoimetric gain corrections and calibration results
R.2015-6 | IVOS recommends to have a workshop of the wider community, after some initial scopign with smaller subgroup
R.2015-7 | IVOS recommends to